## Sheet1
S.No. | Tasks | Assigned | Status | ETA | Remark
1 | Unit of work done along with 1 master child table test | Shambhoo | Pending | 4 hours | In case if 1 table data inserted and another table data not, we should not commit in db. Multiple tables should commit together or should get rollback all.
2 | Token based authentication at WebAPI | Shambhoo | Pending | 4 hours | Each method get called need to be authenticated with a token in encrypted format.
3 | Application level logging | Shambhoo | Pending | Yet to decide
4 | Application level error handling | Shambhoo | Pending | Yet to decide
5 | Account Module | Junaid | Pending | 16 hours
6 | Member ship provider add in project | Junaid | Done | 4 hours
7 | Role based authentication | Junaid | Pending
8 | HTML Wireframes creation (Login, Account, Dashboard, Devices Scanner page etc) | Anith & Tintu | Pending | 16 hours
9 | DB project creation | Shambhoo | Pending | 2 hours
10 | SMTP Code | Tintu | Pending | 8 hours
11 | Encryption/Decryption methods | Tintu | Pending | 4 hours
12 | POC on text read from image | Vipin/Chahlse | Pending | 16 hours
13 | POC on input connected devices like scanner or any kind of devices | Shambhoo | Done | 16 hours
14 | Multi culture application | Tintu | Pending | Yet to decide
15 | Ajax loader start and stop methods |  | Pending | Yet to decide
16 | Save Password | Shambhoo | Pending | Yet to decide
17 | Login --> Texboxes width increase | Junaid | Pending | Yet to decide
18 | Texboxes content place holder | Junaid | Pending | Yet to decide
19 | Form authentication. Redirect to login in case other url hit without login | Shambhoo | Pending | Yet to decide
20 | Toastr for message | Junaid | Pending | Yet to decide
21 | After login failed, no message shown to user. | Junaid | Pending | Yet to decide
22 | Add User/ Manage Users | Junaid | Pending | Yet to decide
23 | Left Side Menu, Role based. | Junaid | Pending | Yet to decide