## Sheet1
S.No. | Tasks | Assigned | Status | Module | ETA | Remark
1 | Unit of work done along with 1 master child table test | Shambhoo | Pending | Common Project Related Tasks | 4 hours | In case if 1 table data inserted and another table data not, we should not commit in db. Multiple tables should commit together or should get rollback all.
2 | Token based authentication at WebAPI | Shambhoo | Pending | Common Project Related Tasks | 4 hours | Each method get called need to be authenticated with a token in encrypted format.
3 | Application level logging | Shambhoo | Pending | Common Project Related Tasks | 4 hours
4 | Application level error handling | Shambhoo | Pending | Common Project Related Tasks | 4 hours
5 | Login Page | Junaid | Done | Account | 4 hours
6 | Member ship provider add in project | Junaid | Done | Account | 4 hours
7 | Role based authentication | Shambhoo | Pending | Account
8 | HTML Wireframes creation (Login, Account, Dashboard, Devices Scanner page etc) | Anith & Tintu | Pending | Common Project Related Tasks | 16 hours
9 | DB project creation | Shambhoo | Pending | Common Project Related Tasks | 2 hours
10 | SMTP Code | Tintu | Pending | Common Project Related Tasks | 8 hours
11 | Encryption/Decryption methods | Tintu | Pending | Common Project Related Tasks | 4 hours
13 | POC on input connected devices like scanner or any kind of devices | Shambhoo | Done | Common Project Related Tasks | 16 hours
14 | Multi culture application | Tintu | Pending | Common Project Related Tasks
15 | Ajax loader start and stop methods |  | Pending | Common Project Related Tasks
16 | Save Password | Vipin | Done | Account
17 | Login --> Texboxes width increase | Vipin | Done | Account
18 | Texboxes content place holder | Vipin | Done | Account
19 | Form authentication. Redirect to login in case other url hit without login | Shambhoo | Done | Account
20 | Toastr for message | Vipin | Done | Common Project Related Tasks
21 | After login failed, no message shown to user. | Vipin | Done | Account
22 | Add User/ Manage Users | Junaid | Done | Account |  | Need testing
23 | Left Side Menu, Role based. | Shambhoo/Vipin | Pending | Account | 4 hours
24 | All sub menus left side should get open first time too | Anith | Pending | Common Project Related Tasks | 1 hour
25 | With the help of MODI library in visitor Management forms, need to save information of ID card into database. | Shambhoo | Pending | Adminstration | 4 hours
26 | Facility Profile Screen | Yet to decide | Pending | Adminstration
27 | Buildings Screen | Yet to decide | Pending | Adminstration
28 | Gates | Yet to decide | Pending | Adminstration
29 | Shift Management | Yet to decide | Pending | Adminstration
30 | Shift Assignment | Yet to decide | Pending | Adminstration
31 | Dashboard | Yet to decide | Pending | Adminstration
32 | Reporting | Yet to decide | Pending | Adminstration
33 | Facebook, Twitter, Integration | Yet to decide | Pending | Account |  | Need to decide with Suraj
34 | Dependency Injection | Shambhoo | Pending | Common Project Related Tasks
24 | In case of any error, login page still show invalid user message | Junaid | Pending | Account
35 | Login background image change | Anith | Done | Account
36 | Sign Out | Vipin | Done | Account
37 | Put logged in user detail in session | Shambhoo | Pending | Account
38 | My Profile Page | Junaid | Pending | Account
39 | Image upload work left -- Add/Edit User | Junaid | Pending | Account